## Roadmap (all)
phase | priority_rank | initiative | objective | domains | linked_findings | critical_high_findings | implementation_effort | expected_risk_reduction_pct | risk_points_removed | owner | quadrant
Days 0-30: Stabilize | 2 | Cloud Exposure Remediation | Remove public storage exposure, enable encryption and harden internet-facing services. | Cloud Security | 11 | 4 | Medium | 33.9 | 53.9 | Cloud Security Lead | Strategic Initiative
Days 0-30: Stabilize | 3 | AI Audit Logging | Structured logging of AI prompts, responses and retrieval to the SIEM. | AI Governance, Security Operations | 6 | 4 | Medium | 48.5 | 53.9 | AI Governance Lead | Strategic Initiative
Days 0-30: Stabilize | 5 | Privileged MFA Enforcement | Enforce phishing-resistant MFA on every privileged account; block legacy auth. | Identity & Access Management | 4 | 2 | Low | 38.2 | 25.8 | IAM Engineering Lead | Quick Win
Days 0-30: Stabilize | 8 | Continuous Cloud Control Monitoring | Azure Policy guardrails with drift detection and lifecycle inventory. | Cloud Security, Security Operations | 10 | 2 | Medium | 30.7 | 42.3 | Cloud Operations Lead | Strategic Initiative
Days 0-30: Stabilize | 11 | AI Data-Loss Prevention | Prompt-side DLP, retrieval allow-lists and data-minimisation reviews for AI pathways. | AI Governance, Privacy & Data Protection | 7 | 3 | High | 40.1 | 49.3 | AI Governance Lead | Strategic Initiative
Days 0-30: Stabilize | 12 | Joiner-Mover-Leaver Automation | Automate de-provisioning from HR; weekly reconciliation of leavers vs. active accounts. | Identity & Access Management | 3 | 2 | Medium | 50 | 27.1 | IAM Engineering Lead | Strategic Initiative
Days 0-30: Stabilize | 14 | Sensitive-Data Protection | Encrypt all Confidential/Restricted data with customer-managed keys. | Privacy & Data Protection | 4 | 2 | Medium | 38.2 | 25.9 | Data Protection Officer | Strategic Initiative
Days 31-60: Govern | 1 | AI Governance Operating Model | AI inventory, ownership, risk tiering, approved use cases and human-oversight rules. | AI Governance | 12 | 2 | Low | 28.7 | 39.5 | AI Governance Lead | Quick Win
Days 31-60: Govern | 4 | Third-Party AI Risk Review | AI-specific vendor risk reviews, data-handling disclosure and supplier oversight. | AI Governance, Governance & Third-Party Risk, Privacy & Data Protection | 14 | 4 | Medium | 29.9 | 52.6 | Third-Party Risk Manager | Strategic Initiative
Days 31-60: Govern | 7 | Technology Risk Governance | Risk ownership, remediation dates, exception approvals and contract review cadence. | Governance & Third-Party Risk | 11 | 0 | Low | 26 | 27.5 | Technology Risk Manager | Quick Win
Days 31-60: Govern | 9 | Privileged Access Modernisation | Just-in-time elevation, separate admin accounts and re-scoped service identities. | Cloud Security, Identity & Access Management | 11 | 2 | Medium | 29 | 36.1 | IAM Engineering Lead | Strategic Initiative
Days 31-60: Govern | 10 | SOC Operating Model Uplift | Alert ownership, severity taxonomy and 12-month log retention. | Security Operations | 6 | 1 | Low | 25.7 | 17.2 | SOC Manager | Quick Win
Days 31-60: Govern | 13 | Sensitive-Data Classification | Re-classify and assign owners for all PII-bearing and sensitive datasets. | Privacy & Data Protection | 7 | 2 | Medium | 31.6 | 26.3 | Data Protection Officer | Strategic Initiative
Days 31-60: Govern | 15 | Data Retention Governance | Define retention for all datasets and auto-purge AI prompt / conversation data. | Privacy & Data Protection | 7 | 0 | Medium | 26.7 | 19.4 | Data Protection Officer | Low Priority
Days 31-60: Govern | 16 | Vulnerability Management Uplift | Enforce a 30-day critical-vulnerability SLA with executive reporting. | Security Operations | 3 | 1 | Medium | 29 | 11.2 | Vulnerability Management Lead | Strategic Initiative
Days 31-60: Govern | 17 | Incident Response Readiness | Runbooks for critical systems and an AI-incident playbook with a tabletop exercise. | Security Operations | 6 | 0 | Medium | 27.2 | 16.3 | Incident Response Lead | Low Priority
Days 31-60: Govern | 18 | IAM Governance Uplift | Assign accountable owners to every privileged account and enforce at creation. | Identity & Access Management | 2 | 0 | Low | 26.5 | 5.2 | IAM Operations Manager | Fill-In
Days 61-90: Scale | 6 | Automated Access Reviews | Stand up quarterly access certification and an automated 90-day dormancy policy. | Identity & Access Management | 8 | 1 | Low | 27.6 | 25.3 | IAM Operations Manager | Quick Win
Days 61-90: Scale | 19 | Cloud Network Segmentation | Private endpoints and default-deny network rules across the tenant. | Cloud Security | 3 | 0 | High | 27 | 8.8 | Cloud Security Lead | Low Priority
Days 61-90: Scale | 20 | AI Output Monitoring | Output-quality, bias and drift monitoring feeding the AI governance forum. | AI Governance | 2 | 0 | Medium | 22.5 | 4.5 | AI Governance Lead | Low Priority

## Stabilize
phase | priority_rank | initiative | objective | domains | linked_findings | critical_high_findings | implementation_effort | expected_risk_reduction_pct | risk_points_removed | owner | quadrant
Days 0-30: Stabilize | 2 | Cloud Exposure Remediation | Remove public storage exposure, enable encryption and harden internet-facing services. | Cloud Security | 11 | 4 | Medium | 33.9 | 53.9 | Cloud Security Lead | Strategic Initiative
Days 0-30: Stabilize | 3 | AI Audit Logging | Structured logging of AI prompts, responses and retrieval to the SIEM. | AI Governance, Security Operations | 6 | 4 | Medium | 48.5 | 53.9 | AI Governance Lead | Strategic Initiative
Days 0-30: Stabilize | 5 | Privileged MFA Enforcement | Enforce phishing-resistant MFA on every privileged account; block legacy auth. | Identity & Access Management | 4 | 2 | Low | 38.2 | 25.8 | IAM Engineering Lead | Quick Win
Days 0-30: Stabilize | 8 | Continuous Cloud Control Monitoring | Azure Policy guardrails with drift detection and lifecycle inventory. | Cloud Security, Security Operations | 10 | 2 | Medium | 30.7 | 42.3 | Cloud Operations Lead | Strategic Initiative
Days 0-30: Stabilize | 11 | AI Data-Loss Prevention | Prompt-side DLP, retrieval allow-lists and data-minimisation reviews for AI pathways. | AI Governance, Privacy & Data Protection | 7 | 3 | High | 40.1 | 49.3 | AI Governance Lead | Strategic Initiative
Days 0-30: Stabilize | 12 | Joiner-Mover-Leaver Automation | Automate de-provisioning from HR; weekly reconciliation of leavers vs. active accounts. | Identity & Access Management | 3 | 2 | Medium | 50 | 27.1 | IAM Engineering Lead | Strategic Initiative
Days 0-30: Stabilize | 14 | Sensitive-Data Protection | Encrypt all Confidential/Restricted data with customer-managed keys. | Privacy & Data Protection | 4 | 2 | Medium | 38.2 | 25.9 | Data Protection Officer | Strategic Initiative

## Govern
phase | priority_rank | initiative | objective | domains | linked_findings | critical_high_findings | implementation_effort | expected_risk_reduction_pct | risk_points_removed | owner | quadrant
Days 31-60: Govern | 1 | AI Governance Operating Model | AI inventory, ownership, risk tiering, approved use cases and human-oversight rules. | AI Governance | 12 | 2 | Low | 28.7 | 39.5 | AI Governance Lead | Quick Win
Days 31-60: Govern | 4 | Third-Party AI Risk Review | AI-specific vendor risk reviews, data-handling disclosure and supplier oversight. | AI Governance, Governance & Third-Party Risk, Privacy & Data Protection | 14 | 4 | Medium | 29.9 | 52.6 | Third-Party Risk Manager | Strategic Initiative
Days 31-60: Govern | 7 | Technology Risk Governance | Risk ownership, remediation dates, exception approvals and contract review cadence. | Governance & Third-Party Risk | 11 | 0 | Low | 26 | 27.5 | Technology Risk Manager | Quick Win
Days 31-60: Govern | 9 | Privileged Access Modernisation | Just-in-time elevation, separate admin accounts and re-scoped service identities. | Cloud Security, Identity & Access Management | 11 | 2 | Medium | 29 | 36.1 | IAM Engineering Lead | Strategic Initiative
Days 31-60: Govern | 10 | SOC Operating Model Uplift | Alert ownership, severity taxonomy and 12-month log retention. | Security Operations | 6 | 1 | Low | 25.7 | 17.2 | SOC Manager | Quick Win
Days 31-60: Govern | 13 | Sensitive-Data Classification | Re-classify and assign owners for all PII-bearing and sensitive datasets. | Privacy & Data Protection | 7 | 2 | Medium | 31.6 | 26.3 | Data Protection Officer | Strategic Initiative
Days 31-60: Govern | 15 | Data Retention Governance | Define retention for all datasets and auto-purge AI prompt / conversation data. | Privacy & Data Protection | 7 | 0 | Medium | 26.7 | 19.4 | Data Protection Officer | Low Priority
Days 31-60: Govern | 16 | Vulnerability Management Uplift | Enforce a 30-day critical-vulnerability SLA with executive reporting. | Security Operations | 3 | 1 | Medium | 29 | 11.2 | Vulnerability Management Lead | Strategic Initiative
Days 31-60: Govern | 17 | Incident Response Readiness | Runbooks for critical systems and an AI-incident playbook with a tabletop exercise. | Security Operations | 6 | 0 | Medium | 27.2 | 16.3 | Incident Response Lead | Low Priority
Days 31-60: Govern | 18 | IAM Governance Uplift | Assign accountable owners to every privileged account and enforce at creation. | Identity & Access Management | 2 | 0 | Low | 26.5 | 5.2 | IAM Operations Manager | Fill-In

## Scale
phase | priority_rank | initiative | objective | domains | linked_findings | critical_high_findings | implementation_effort | expected_risk_reduction_pct | risk_points_removed | owner | quadrant
Days 61-90: Scale | 6 | Automated Access Reviews | Stand up quarterly access certification and an automated 90-day dormancy policy. | Identity & Access Management | 8 | 1 | Low | 27.6 | 25.3 | IAM Operations Manager | Quick Win
Days 61-90: Scale | 19 | Cloud Network Segmentation | Private endpoints and default-deny network rules across the tenant. | Cloud Security | 3 | 0 | High | 27 | 8.8 | Cloud Security Lead | Low Priority
Days 61-90: Scale | 20 | AI Output Monitoring | Output-quality, bias and drift monitoring feeding the AI governance forum. | AI Governance | 2 | 0 | Medium | 22.5 | 4.5 | AI Governance Lead | Low Priority